## Slide 1: Run2b Silicon Detector
Design goals of Run2b Si system
Stave design
Silicon sensors
Schedule
K. Hara (U. Tsukuba)
K. Hara (U. Tsukuba)

## Slide 2: Design goals of Run2b silicon
Performance as good as/better than Run2a system
Simple and robust*, to be ready by summer 2004
No changes for DAQ chains
new (Si, chip-hybrid, mini-portcard, Junction PC)
SVX3 chips: Honeywell! (cost, yield), noise@large Cdet
SVX4 chips: 0.25μm process, 2.5V, submitted before Christmas
Fine-pitch hybrid (BeO) developed for L00
Eliminate rad-critical (~5.7fb-1)DOIMs in Run2a portcard
*Uniform stave design(~90%)+special inner layer+a la L00
Minimum use of light-weight cables

## Slide 3: 6-fold layout
163.5R
6-fold wedge SVT
90°@L1,2,5
good anchor to COT
good ΔZ for 3D impact param
106.5R(SVX2a)
L1 axial coverage~0.7?

## Slide 4: Descoping?
Use outer staves for L1
Drop L4 or L5
4%change
~3 GeV less MH reach
~14% more L

## Slide 5: RunIIB Stave
Peek tube
water channel
cable bus
Silicon detector
hybrid substrate
readout chip
pitch adapter
C fiber
Stave structure (60 cm long, supported at z=0 and ±60cm):
  Carbon fiber – rohacell structure with ~2x6 mm peek cooling pipes
  On each side:
    6 single sided silicon sensors
    3 hybrids glued to the silicon.
  Silicon glued to copper-kapton bus cables
  Hybrids wirebonded to bus cables
Mini Portcard

## Slide 6: RunIIB Stave

## Slide 7: Number of Sensors
Outer axial (75um) 1008
°(93um) 504
2.5°(80um) 504
3 types 2016
Inner axial 144
axial’ 72
° 72
3 types 288
?
Micron
HPK:2300+spares=2700
(13+α)months @+200/mo
90
90

## Slide 8: Si sensor : R&D issue
Axial and SAS sensors are similar to ATLAS
90°on 6” process is new
via
SiO2 insulator
Previously achieved:
~4μm (4” SSDM)
~5μm (4” DSDM)
? (6” SSDM)

## Slide 9: Schedule
2002
2003
2004
mechanical prototypes(Mar~May)
electrical prototypes(~Sept)
stave production
barrel assembly
Si prototypes
90deg R&D
final tests
order production Si
series Si delivery
SVX4, cables, others
Schedule risks: (1) SVX4 chip (for electrical prototyping, reliability)
successful operation w/ bus cable
(2) installation in 6-mon shutdown
Contingency ~6 months
Shutdown
(6months)
full production(200d)